## WHMcNumber (hidden)
DO NOT ALTER OR DELETE THIS SHEET. | Chart Names | Excel Version | 12

## A3 Thinking
A3 PROJECT MANAGEMENT AND PROBLEM SOLVING THINKING
1. | WHAT IS AN A3 PROJECT?
An activity that
(a) supports achievement of the continuous improvement objectives
(b) requires > 20 hours dedicated man-hours
(c) has an A3 worksheet
2. | WHERE DO A3 PROJECTS COME FROM?
All functions & all personnel entitled to propose projects
Derived from e.g. continuous improvement objectives or VSM or other business critical source e.g. compliance requirement or safety requirement
All projects pre-screened by snr managers prior to proposal for the master list
The master project list is maintained by the continuous improvement facilitator
3. | A3 OBJECTIVE
To provide a one page (A3, 420mm x 297mm) summary of a programme, project or problem, for the project team & relevant personnel within the organisation
4. | WHY?
Encourages brevity & sharpness of thinking
Tells a logical story on one sheet for all viewers
Provides a common organisation-wide format for all programme, management, project managment & problem solving activities
5. | WHO?
Team leader of the programme or project, or process owner of the area under review
6. | HOW?
Completion of the standard A3 Template. The template usually consistes of 7 to 9 boxes with standard input requirements, that follow the 8 stpe path. The template is modified to suit individual projects.
Use photographs, drawings & graphs to tell the story
7. | UPDATE FREQUENCY
The A3 is a living document and is updated as the team moves through the stages of the project
8. | REVIEW FREQUENCY
The A3 document is reviewed by the team and programme or project champion on an as-required basis during the project lifespan. Review frequencies are determined at the start of the project.

## A3 Steps
TOYOTA 8 STEP PROBLEM SOLVING PROCESS
Step and objective | Tools used
Step 1: Clarify the Problem
Why am I looking at this problem? What is the problem? Who is interested in the problem? What benefit does solving this problem have for me? How does it help to address the goals of the business? | Voice of the customer
Stakeholder analysis
Is/is not analysis
Step 2: Breakdown the Problem
What is the size of the problem? What data do I have? What are the component parts of this problem? How much will I address at this point? | Tree breakdown and process
Step 3: Set the Target.
What outcome do I want? Visualise the desired results. Using the data, set a measurable and realistic goal. | Goal setting. Agreement with stakeholders on outcome
Step 4: Analyse the Root Cause
Clarify the root cause. Consider as many potential cause factors as possible. | Interviews, 5 whys, cause and effects analysis, regression & correlation, process capability analysis
Step 5: Develop Countermeasures
List as many potential countermeasures as possible. Identify an effective countermeasure that directly addresses the root cause. | Brainstorming
Options Matrix
Step 6: Pick a Countermeasure and implement
Select the most practical and effective countermeasure. Create a clear and detailed action plan. Implement quickly. | Action plan
Gantt chart
Step 7: Monitor Results & Process
Monitor progress and report findings to stakeholders. It may require more than one attempt to get the desired result. Mistakes are an important part of the learning process. | Run chart, control chart
Step 8: Standardise & Share Success
Document the new process and set as new standard. Share the new standard through Horizontal deployment. Reflect and celebrate success. Start the next Improvement! | Standard work
Current Condition
Paneer cheeseburger cream cheese. Queso fromage who moved my cheese camembert de normandie cheesy feet parmesan cheese on toast cut the cheese. Cheesecake red leicester mascarpone hard cheese babybel cut the cheese manchego mozzarella.
Target Condition
Veggies es bonus vobis, proinde vos postulo essum magis kohlrabi welsh onion daikon amaranth tatsoi tomatillo melon azuki bean garlic. Gumbo beet greens corn soko endive gumbo gourd.
GAP
Esse chillwave fashion axe messenger bag echo park. Culpa disrupt plaid pariatur nostrud.
Root
Total.
Issue 1
Quantity 1
Issue 2
Quantity 2
Issue N
Quantity N
Issue 1.1
Quantity 11
Issue 1.2
Quantity 12
Issue 2.1
Quantity 21
Issue 2.2
Quantity 22
Issue N.1
Quantity N1
Issue N.2
Quantity N2
Process 1
Process 2
Process 3
Process 4
Process 5
Process 6
Point of Occurrence

## A3 Template
A3 No. and Name |  | Team members (name & role) |  | Stakeholders (role & department) |  | Company objective
Team 7 |  | 1. | Dhruv | 1. | AI & ML Coordinator, Conestoga College
|  | 2. | Ankit | 2. | Potential Client name(s)
Team Leader (name & 'phone ext) |  | 3. | Jimit | 3. | Other Conestoga College stakeholder(s) | Start date & planned duration
|  | 4. | Jay and vishal | 4.
1. Clarify the problem |  |  |  | 4. Analyse the Root Cause |  |  | 7. Monitor Results & Process
2. Breakdown the problem
8. Standardise & Share Success
5. Develop Countermeasures
6. Implement Countermeasure
3. Set the Target
1 | Reduce the number of derivative traders experiencing losses from 90% to 70% within 3 months
2 | Deliver personalized trading education modules
3 | Achieve a 50% increase in stop-loss compliance
4
Your team logo and project name
Note on B2: use standard project numbering system (e.g. 2011-XX) and simple short name
Note on B8: 1. Clarify the problem Why am I looking at this problem? What is the problem? Who is interested in the problem? What benefit does solving this problem have for me? How does it help to address the goals of the business? Select the area/process & open A3 in Excel Elect a leader Form the team (stakeholders) Train the team in the 8 step approach Identify all stakeholders Define the problem in terms of impact on the customer & stakeholders. Conduct is/is not analysis Conduct a gemba walk and take photographs
Note on H8: 4. Analyse the Root cause Clarify the root cause. Consider as many potential cause factors as possible. - Interviews - praetor charts - Data stratification - 5 whys - Cause and effects analysis - Process Capability Analysis - Scatter diagrams - Box plots - Regression & Correlation - FMEA Identify areas for improvement
Note on N8: 6. Monitor Results & Process Monitor progress and report findings to stakeholders. It may require more than one attempt to get the desired result. Mistakes are an important part of the learning process. - Run chart - Control chart - Process capability analysis Conduct post implementation review - snag list & action items
Note on B22: 2. Breakdown the problem What is the size of the problem? What data do I have? What are the component parts of this problem? How much will I address at this point? Draft a summary map of process, or machine schematic e.g. - SIPOC - Spaghetti map - process map - blueprint Measure key features of the process problem e.g. - Bar chart - line graph - Run chart
Note on N27: 8. Standardise & Share Success Document the new process and set as new standard. Share the new standard through Horizontal deployment. Reflect and celebrate success. - Train personnel in new way of doing things - Standardise new processes, update procedures, implement visual management - Use control charting to prove results and maintain discipline in th area - Confirm the financial gains (if required) - Present to senior management - Recognise and reward the team - Reflect on lesson learned Start the next Improvement!
Note on H33: 5. Develop Countermeasures List as many potential countermeasures as possible. Identify an effective countermeasure that directly addresses the root cause. Prioritise issues Identify and make ready all tools an equipment for change in advance of the of the event - Brainstorming - Options Matrix
Note on H42: 5. Pick a Countermeasure & implement Select the most practical and effective countermeasure(s). Create a clear and detailed action plan. Implement quickly. - Gantt chart - tasks and timelines - Detailed timetable of events - Roadmap - Backlog items
Note on B44: 3. Set the target What outcome do I want? Visualise the desired results. Using the data, set a measurable and realistic goal. Goal format: Action verb + object of the action + from "current state" + to "future state" by "date" e.g. Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 January 2014" Draft the outline project plan by when the project will be finished Allocate time lines & responsibilities (e.g. summary Gantt chart) Develop draft financial gains and get finance approval (if appropriate)